## Slide 1
90-Day AI Readiness Implementation Plan
From assessment to first measurable outcome
© 2026 Aiprosol Ltd · Enterprise AI Readiness Assessment Kit

## Slide 2
Three phases
Foundation → Pilot → Scale
• Phase 0 (Days 1-30) — Foundation: alignment, governance, baseline measurement
• Phase 1 (Days 31-60) — Pilot: 1 high-leverage use case, end-to-end in production
• Phase 2 (Days 61-90) — Scale: 3 more use cases, repeatable playbook
Aiprosol Enterprise AI Readiness · 90-Day Implementation Plan

## Slide 3
Phase 0 · Foundation (Days 1-30)
Get alignment + measure baseline
• Day 1-7: Stakeholder alignment (CEO + CIO + line-of-business head)
• Day 8-14: Run the 120-question Readiness Scorecard with affected teams
• Day 15-21: Identify top 3 candidate use cases via Opportunity Map
• Day 22-28: Select 1 use case for pilot (highest ROI × lowest risk)
• Day 29-30: Sign-off on success criteria + check-in cadence
Aiprosol Enterprise AI Readiness · 90-Day Implementation Plan

## Slide 4
Phase 0 · Roles
• Executive sponsor — accountable for outcome
• Pilot lead — runs daily standup, manages timeline
• Domain expert — has the operational context
• Technical lead — implements the workflow
• Change champion — manages stakeholder comms
Aiprosol Enterprise AI Readiness · 90-Day Implementation Plan

## Slide 5
Phase 0 · Deliverables
• Completed Readiness Scorecard (all 120 questions)
• Opportunity Map (top 5 use cases ranked by value × feasibility)
• Signed-off pilot charter (use case, success criteria, timeline, budget)
• Vendor RFP (if external tooling needed)
• Communications plan
Aiprosol Enterprise AI Readiness · 90-Day Implementation Plan

## Slide 6
Phase 1 · Pilot (Days 31-60)
Ship one use case end-to-end
• Day 31-37: Set up tooling + integrations
• Day 38-49: Build the workflow with humans-in-the-loop (Phase 1 of the 3-phase progression)
• Day 50-56: Move to Phase 2 (auto with override) once quality is proven
• Day 57-60: Measure baseline vs after; document learnings
Aiprosol Enterprise AI Readiness · 90-Day Implementation Plan

## Slide 7
Phase 1 · Success criteria
• Quantitative outcome achieved (e.g., hours saved / week)
• Quality maintained or improved (vs manual baseline)
• Zero security or compliance incidents
• Adoption by intended users >80%
• Total time-to-value documented for replication
Aiprosol Enterprise AI Readiness · 90-Day Implementation Plan

## Slide 8
Phase 1 · Risks to manage
• Scope creep — adding 'just one more' use case before the first works
• Quality regression — moving to auto before quality is proven
• Adoption resistance — solve with champion + visible wins
• Cost surprises — set up cost monitoring before launch
• Vendor lock-in — keep an exit plan in mind from Day 1
Aiprosol Enterprise AI Readiness · 90-Day Implementation Plan

## Slide 9
Phase 2 · Scale (Days 61-90)
Repeat with 3 more use cases + build muscle memory
• Day 61-67: Document pilot's playbook (the repeatable steps)
• Day 68-74: Begin use cases #2-#3 in parallel (different teams, similar pattern)
• Day 75-81: Begin use case #4 (start to test cross-system patterns)
• Day 82-90: Quarterly business review — what to scale next, what to retire
Aiprosol Enterprise AI Readiness · 90-Day Implementation Plan

## Slide 10
Phase 2 · Compounding
• Cross-workflow data: signals from one workflow feed another
• Shared infrastructure: common LLM endpoints, prompt library, vector store
• Shared learnings: weekly retro across pilot teams
• Shared metrics: same dashboards across use cases
Aiprosol Enterprise AI Readiness · 90-Day Implementation Plan

## Slide 11
90-day outcomes you should expect
• 4 working AI-augmented workflows in production
• Documented playbook for the next 10
• Measured baseline + improvement for each
• Team aligned + confident on next phase
• Defensible business case for year-2 investment
Aiprosol Enterprise AI Readiness · 90-Day Implementation Plan

## Slide 12
Year-2 horizon (preview)
• Move from 4 → 30 workflows with the same team size
• Begin internal AI centre of excellence
• Take learnings to executive education + board
• Look for category-defining moves (not just optimisation)
Aiprosol Enterprise AI Readiness · 90-Day Implementation Plan

## Slide 13
Common 90-day pitfalls
• Trying to fix governance + pilot a use case + train teams all in Day 1
• Picking too big a pilot ('let's automate all of sales')
• Selecting tools before defining the problem
• Underinvesting in change management
• Declaring victory before measuring outcomes
Aiprosol Enterprise AI Readiness · 90-Day Implementation Plan

## Slide 14
Aiprosol contact
When you need expert help
• hello@aiprosol.com
• aiprosol.com
• Srijan Paudel, Founder
Aiprosol Enterprise AI Readiness · 90-Day Implementation Plan