## Slide 1
90-Day AI Implementation Plan
Phase 0 → Phase 1 → Phase 2
Aiprosol · Enterprise AI Readiness Kit · 2026

## Slide 2
Summary KPIs
Target outcomes over 90 days
• Top-3 workflows live in production by day 60
• Average response time on key process reduced by 70%+
• Hours reclaimed per week: 30+ across pilot cohort
• 100% of relevant staff trained by day 90
• Annual cost savings: $250k–$1M (mid-size org baseline)
Aiprosol · Enterprise AI Readiness Kit

## Slide 3
Today's Baseline
From the Readiness Scorecard
• Overall readiness score: [INSERT FROM SCORECARD] / 100
• Strongest dimensions: [TOP 3]
• Weakest dimensions: [BOTTOM 3 — these are our 90-day focus]
• Current SaaS spend on automation: $[INSERT] / mo
• Estimated automation candidates from audit: [INSERT] workflows
Aiprosol · Enterprise AI Readiness Kit

## Slide 4
Selected Vendors
Output of RFP scoring
• [Vendor 1] — primary platform — score [X]/200
• [Vendor 2] — secondary / specialised — score [X]/200
• Rationale: [why this combination]
• Contract terms: [duration, $$ committed, exit clauses]
• Implementation partner: Aiprosol (or other) for first 90 days
Aiprosol · Enterprise AI Readiness Kit

## Slide 5
Phase 0 — Foundations (Days 0–14)
Set the stage for execution
• Week 1: SSO wiring, DPA execution, security review
• Week 1: Data audit on top-3 datasets needed for pilot
• Week 2: Pilot user cohort selected (8–15 users across 2–3 teams)
• Week 2: Success criteria documented + baselined per workflow
• Output: production access · 5-min usage walkthrough complete · baselines logged
Aiprosol · Enterprise AI Readiness Kit

## Slide 6
Phase 0 Risks
What can go wrong + mitigation
• Risk: SSO integration delays · Mitigation: backup local accounts for first 2 weeks
• Risk: DPA legal back-and-forth · Mitigation: standard contract pre-approved
• Risk: pilot cohort drops out · Mitigation: 2x oversubscribe, recruit champions
• Risk: baseline data not available · Mitigation: instrument week 0
Aiprosol · Enterprise AI Readiness Kit

## Slide 7
Phase 1 — Pilot (Days 15–45)
First 3 workflows in production
• Week 3–4: Workflow 1 built + tested + shipped to pilot cohort
• Week 4–5: Workflow 2 built + shipped
• Week 5–6: Workflow 3 built + shipped
• Daily: Slack-pinged metrics to leadership channel
• Weekly: 30-min cohort interview cadence
• Output: 3 workflows running · hours-reclaimed metric trending · 5+ user testimonials
Aiprosol · Enterprise AI Readiness Kit

## Slide 8
Phase 1 Risks
What can go wrong + mitigation
• Risk: workflow latency higher than expected · Mitigation: caching layer + async patterns
• Risk: AI accuracy below threshold · Mitigation: human-in-the-loop fallback
• Risk: pilot users disengage · Mitigation: weekly office hours + champion model
• Risk: budget overrun · Mitigation: weekly cost reports + hard stop at 110%
Aiprosol · Enterprise AI Readiness Kit

## Slide 9
Phase 2 — Scale (Days 46–90)
Roll out to wider org
• Week 7–8: Onboard remaining users (training, runbook handoff)
• Week 9–10: Add workflows 4–10 based on pilot feedback
• Week 11–12: Governance launch — AI policy, training programme, escalation paths
• Week 13: 90-day review + decision on Phase 3 (year 1 roadmap)
• Output: 100% relevant staff onboarded · 10+ workflows live · monthly governance review cadence
Aiprosol · Enterprise AI Readiness Kit

## Slide 10
Phase 2 Risks
What can go wrong + mitigation
• Risk: change fatigue across org · Mitigation: phased rollout, no more than 2 changes/team/month
• Risk: governance theatre (rules without enforcement) · Mitigation: monthly audit cadence
• Risk: customer-facing AI errors · Mitigation: clear escalation + correction loop
• Risk: vendor scope creep · Mitigation: change control board
Aiprosol · Enterprise AI Readiness Kit

## Slide 11
Talent Plan
Roles needed across the 90 days
• AI Workflow Specialist: 0.5 FTE (internal or Aiprosol-supplied)
• Implementation Engineer: 1.0 FTE during Phase 0–1
• Workflow Operator(s): 0.2 FTE per workflow ongoing
• Auditor / governance owner: 0.1 FTE ongoing
• Executive sponsor: 1 hour / week, day-90 review owner
Aiprosol · Enterprise AI Readiness Kit

## Slide 12
Governance + Audit Framework
Established by Day 60
• AI Usage Policy: published, signed by every staff member with AI access
• Vendor approval workflow: new tool proposals reviewed bi-weekly
• Output review: random 1% sampled monthly, accuracy tracked
• Incident response: documented runbook + 24h SLA on customer-facing issues
• Quarterly board review of AI initiatives + outcomes
Aiprosol · Enterprise AI Readiness Kit

## Slide 13
Financial Model
Cost vs. reclaim across the 90 days
• Phase 0 cost: licenses + setup ≈ $15–30k
• Phase 1 cost: implementation + integration ≈ $30–80k
• Phase 2 cost: training + governance launch ≈ $20–40k
• Total: $65–150k investment over 90 days
• Expected reclaim by Day 90: 30+ hours / week across pilot cohort
• 12-month projected savings: $250k–$1M (depends on org size + scope)
Aiprosol · Enterprise AI Readiness Kit

## Slide 14
Day-90 Review Template
Decision points + next steps
• Workflows live: [N] of 10 target
• Hours reclaimed / week: [X] vs target [Y]
• User adoption: [%] of intended cohort
• Cost vs budget: [%] of envelope used
• Top 3 wins · Top 3 lessons · Top 3 risks for next quarter
• Phase 3 decision: scale (yes / yes-with-changes / no — and what next)
Aiprosol · Enterprise AI Readiness Kit